## Backlog
Function/Screen/Use Case | Level | Front End | Back End | Sprint | Week
Authentication - Login | Simple | An | An | 1 | 3
Authentication - Register | Medium | An | An | 1 | 3
JWT Authentication Setup | Medium | An | An | 1 | 3
Role-Based Authorization | Complex | An | An | 1 | 3
Account Approval Management | Medium | Toàn | Toàn | 1 | 3
Authentication - Forgot Password | Simple | Toàn | Toàn | 1 | 3
Authentication - Change Password | Simple | Toàn | Toàn | 1 | 3
Authentication - Logout | Simple | Toàn | Toàn | 1 | 3
User Profile Management | Simple | Kiệt | Kiệt | 1 | 3
Create Hackathon Event | Medium | Kiệt | Kiệt | 1 | 4
Category / Track Management | Medium | Kiệt | Kiệt | 1 | 4
Round Management | Medium | Kiệt | Kiệt | 1 | 4
Round Advancement Rule Configuration | Medium | Ngôn | Ngôn | 1 | 4
Team Management - Create Team | Medium | Ngôn | Ngôn | 1 | 4
Team Invitation & Join Team | Complex | Ngôn | Ngôn | 1 | 4
Team Member Management | Medium | Ngôn | Ngôn | 1 | 4
Team Validation Rules (3–5 Members) | Medium | An | An | 1 | 4
Submission Management | Medium | Kiệt | Kiệt | 2 | 5
Submission Validation | Medium | Kiệt | Kiệt | 2 | 5
Submission History | Simple | Kiệt | Kiệt | 2 | 5
GitHub/GitLab Metadata Integration (Optional) | Medium | Toàn | Toàn | 2 | 5
Judge Assignment | Complex | Toàn | Toàn | 2 | 5
Guest Judge Account Management | Medium | Toàn | Toàn | 2 | 5
Mentor Assignment | Medium | Toàn | Toàn | 2 | 5
Judge Dashboard | Medium | Ngôn | Ngôn | 2 | 6
Mentor Dashboard | Medium | Ngôn | Ngôn | 2 | 6
Score Input Form | Complex | Ngôn | Ngôn | 2 | 6
Criterion-Level Score Recording | Complex | Ngôn | Ngôn | 2 | 6
Scoring Criteria Management | Medium | An | An | 2 | 6
Criteria Template Management | Medium | An | An | 2 | 6
Score Finalization | Medium | An | An | 2 | 6
Audit Log & Activity Tracking | Medium | An | An | 2 | 6
Ranking Calculation | Complex | An | An | 3 | 7
Result Qualification Calculation | Complex | An | An | 3 | 7
Promotion To Next Round | Complex | An | An | 3 | 7
Elimination Management | Medium | An | An | 3 | 7
Export Anonymized Scoring Dataset (RBL) | Medium | Ngôn | Ngôn | 3 | 7
Notification & Announcement | Medium | Ngôn | Ngôn | 3 | 7
UI/UX Refinement | Simple | Ngôn | Ngôn | 3 | 7
Result Publication | Medium | Kiệt | Kiệt | 3 | 8
Export CSV/Excel Report | Medium | Kiệt | Kiệt | 3 | 8
Judge Score Variance Dashboard (RBL) | Complex | Kiệt | Kiệt | 3 | 8
Award Management | Medium | Toàn | Toàn | 3 | 8
Calibration Session Management (RBL) | Medium | Toàn | Toàn | 3 | 8
Calibration Score Input (RBL) | Medium | Toàn | Toàn | 3 | 8
Calibration Analytics (RBL) | Medium | Toàn | Toàn | 3 | 8
System Integration & UAT | Complex | All Members | All Members | 3 | 9
QA Testing & Bug Fixing | Complex | All Members | All Members | 3 | 9
Final Deployment | Medium | All Members | All Members | 3 | 9